## Test Cases
| Product Name |  | Managerium , iPOS (SQA) , devprincrbazar, https://devpanel.ibos.io/ |  | TC Start Date |  | 2024-11-19 |  | TEST CASE SUMMARY |  |  | Out of Scope
| Module Name |  | All |  | TC End Date |  |  |  | PASS | 119 | 1. Web - After login many times it faces Page Error/This site can't be reach
[5 empty] | Browser Tested |  |  |  | FAIL | 0 | 2. Mobile App - After login location Access popup appear every moment when change tabs
| Browser |  | microsoft edge, google chrome, firefox |  | Performance Tested |  |  |  | Out of scope | 0 | 3.Web - When operating from one feature/process to another feature/process the Web page goes blank and is not visible even after reloading.
| Test Case Developed & Executed By |  | Tanmoy Datta |  | Developer Name |  | Akash, Polash, Debasree, Bulbul, safat,saymun,shakib |  | Total | 119 | 4.Dev Web- too slow sometimes
5. Multiple API calls when network is in slow 3G
Date | Module/Feature Name | Sub feature | Priority | Test Case ID | Test Cases | Test Type | Test Steps | Test Data | Screenshot | Expected Result | Actual Result | Status | Sprint | Task NO.
| LC margin Details rearrange | [10 empty] | Pass
2024-11-19 | LC Management | Create LC Margin | High | TC_001 | Try to LC Create | Functional Testing | Account->LC Management->LC Create->fill up the form-> save | Office Name: MGM Head Office LC NO: 999901 LC Opening Date: 18-11-2024 PI NO:999901 PI Date:18-11-2024 Purchase Order NO:PO-M240400042 | https://prnt.sc/xTOlYcWhE7z6 | LC Create should be created. | As Expected. | Pass
| LC Management | LC details | High | TC_002 | Try to showing LC details list in LC details page |  | Account->LC Management->LC Details | N/A |  | LC Details list should be showing | As Expected. | Pass
| LC Management | Create LC Margin | High | TC_003 | Try to LC Margin Create | Functional Testing | Account->LC Management->LC Margin->LC Margin Create->fill up the form-> save | Date: 11/18/2024 Office: MGM Head Office LC NO:999901 Bank: AB BANK LTD Bank Acc. No: 1234([AB BANK LTD]) | https://prnt.sc/t8KyN4sMAgK7 | LC Margin Create should be created. | As Expected. | Pass
| LC Management | LC Margin | High | TC_004 | LC Margin details page in showing LC Margin list | UI Testing | Account->LC Management->LC Margin | N/A |  | LC Margin list should be showing | As Expected. | Pass
| LC Management | LC Margin | High | TC_005 | Try to LC Margin Add deposit type | Functional Testing | Account->LC Management->LC Margin->Action(Add Margin)->fill up the form->save | Date: 11/18/2024 Office: MGM Head Office Type: Deposit Accounts Head:Cash in hand Amount:4 | https://prnt.sc/Hfz8bY_5IB_v | LC Margin deposit type should be add LC Margin. | As Expected. | Pass
| LC Management | LC Margin | High | TC_006 | Try to LC Margin Add Adjustment type | Functional Testing | Account->LC Management->LC Margin->Action(Add Margin)->fill up the form->save | Date: 11/18/2024 Office: MGM Head Office Type: Adjustment Accounts Head:Cash in hand Amount:7 | https://prnt.sc/Zlbc-FRdBO7_ | LC Margin Adjustment type should be add LC Margin. | As Expected. | Pass
| LC Management | Accounting Journal | High | TC_007 | Checking LC margin amount Deposit against Transaction Number | Functional Testing | Account->Accounting Journal>Trans Number | Trans Number: JV-M241100297 | https://prnt.sc/8CTPMKtcpFDG | Account Journal Details showing should be LC margin amount Deeposit against | As Expected. | Pass
| LC Management | Accounting Journal | High | TC_008 | Checking LC margin amount Adjustment against Transaction Number | Functional Testing | Account->Accounting Journal>Trans Number | Trans Number: JV-M241100298 | https://prnt.sc/BmDE_xPqnxrB | Account Journal Details showing should be LC margin amount Adjustment against | As Expected. | Pass
2024-11-21 | Account | LC Management | High | TC_009 | Checking specific LC margin Details showing in page | Functional Testing | Account->LC Management->LC Margin->Action(view) | Margin Code: LCM-M241100016 LC No: 999901 Bank Name: AB Bank Bank Acc. No: 1234 | https://prnt.sc/vIzDwFFO4u2_ | LC Margin Details should be showing. | As Expected. | Pass
| Production |  | High | TC_010 | [7 empty] | Pass
| Production | Bill of Material | High | TC_010 | Try to Bill of Material Create | Functional Testing | Production->Bill of Material->create Bill of Material->Multiple Output->save | BOM Name: Test demand One Department: QA Section:QA Section 2 Production Item Information-Item Type:Finished/Trading Goods FG/SFG Item: ITM-00276 - Zigjag Biscuit (Packet) Lot Size: 1 Cost Percentage: 100 Material Item Information- Item Type: Raw Material Material Item: Jipper Quantity : 7 PCS Material Item: Collar Bone Quantity : 3 PCS Material Item: Interlining Charcoal Quantity : 2 YDS | https://prnt.sc/tylgGbD9to0y | Bill of Material Create should be successfully. | As Expected. | Pass
| Production | Bill of Material | High | TC_011 | Bill of Material list showing Bill of Material page | UI Testing | Production->Bill of Material | N/A |  | Bill of Material create list should be showing | As Expected. | Pass
| Production | Bill of Material | High | TC_012 | Checking specific Bill Of Material Details in page | UI Testing | Production->Bill of Material->Action view | BOM Nam:Test Demand One | https://prnt.sc/CdSjTxfBba3z | specific Bill Of Material Details should be showing | As Expected. | Pass
| Production | Bill of Material | High | TC_013 | Checking specific Bill Of Material Edit | Functional Testing | Production->Bill of Material->Action view->Edit->fill up the form->save | Department:Software Engineer Section:Product | https://prnt.sc/53bfEa-nfrZf | Bill Of Material should be Edited successfully | As Expected. | Pass
| Production | Bill of Material | High | TC_014 | Checking specific Bill Of Material Production Item Name edit | Functional Testing | Production->Bill of Material->Action view->Edit->fill up the form->save | Item Name: ITM-00276 - Zigjag Biscuit (Packet) | https://prnt.sc/JcBvpQO1uG5R | Bill Of Material Production Item Name should be Edited successfully | As Expected. | Pass
| Production | Bill of Material | High | TC_015 | Checking After edit specific Bill Of Material | UI Testing | Production->Bill of Material->Action view | N/A | https://prnt.sc/Pis-r2USPuTN | Edited Bill Of Material should be Showing | As Expected. | Pass
| Production | Bill of Material | High | TC_016 | Checking Bill Of Material specific Department and Section wise | Functional Testing | Production->Bill of Material->Select Department->Select Section | Department:Software Engineer Section:Product | https://prnt.sc/dtJ2NR84fbD7 | specific Department and Section wise Bill Of Material should be Showing | As Expected. | Pass
| Sales | Sales Order | High | TC_017 | Try to Create Sales Order | Functional Testing | Sales->sales order->Create Sales Order->fill up the form->save | Create Date:11/20/2024 Office: MGM Head Office Select Customer:PRT-M0272 - ABCD (017155555885) Ship To:ABCD [ Dhaka ] Contact To:ABCD Sales Force:Asif Hasan Type:Sales Exp. Delivery Date:11/20/2024 Project/Outlet/Ref. :ABCD Remarks: Tested by sales order Item Type:Finished/Trading Goods Price Type: Dealer Price Item: ITM-00276 - Zigjag Biscuit (Packet) Quantity (Packet)-2 | https://prnt.sc/1nfoh6KG-vnW | Create Sales Order Create should be successfully. | As Expected. | Pass
| Sales | Sales Order | High | TC_018 |  | UI Testing | Sales->sales order |  |  |  |  | Pass
|  | " " |  | TC_019 | [7 empty] | Pass
| Rearrenge and add transation and account name column in Loan details |  | High | TC_020 | [7 empty] | Pass
| Account | Finance and Banking | High | TC_021 | Try to Loans Create | Functional Testing | Account->Finance and Banking->Loans->Create Loans->fill up the form-> save | Date:11/20/2024 Office:MGM Head Office Type:Long Terms Organization Name:AAA Account No :100000000999 e:11/01/2024 To Date:11/30/2024 General Ledger:Long Terms Loan | https://prnt.sc/MWA6tEe-oQ_1 | Loans request should be created. | As Expected. | Pass
| Account | Finance and Banking | High | TC_022 | Loans list showing Finance and Bankingin Loans page | UI Testing | Account->Finance and Banking->Loans | N/A | https://prnt.sc/DXMFGVtUDH9U | Loans create list should be showing | As Expected. | Pass
| Account | Finance and Banking | High | TC_023 | Checking specific Loans Account Details in page | Functional Testing | Account->Finance and Banking->Loans>Action view | Account No100000000999 | https://prnt.sc/VwuAmbagn7Gn | specific Loans Account should be showing | As Expected. | Pass
| Account | Finance and Banking | High | TC_024 | Long Terms loan Add Adjustment loan in account | Functional Testing | Account->Finance and Banking->Loans>Action Add Adjustment ->fill up form->save | Date:11/20/2024 Office:MGM Head Office Type:Loan Accounts Head:FDBL: 00999 Amount:5 Remarks:test 1 |  |  | As Expected. | Pass
| Account | Finance and Banking | High | TC_025 | Long Terms loan Add Adjustment Refund in account | Functional Testing | Account->Finance and Banking->Loans>Action Add Adjustment ->fill up form->save | Date:11/20/2024 Office:MGM Head Office Type:Refund Accounts Head:EBL: 454545 Amount:5 Remarks:test 2 |  |  | As Expected. | Pass
| Account | Accounting Journal | High | TC_026 | checking Long Terms loan Account Number Add Adjustment Journal Approval pending voucher | UI Testing | Account->Accounting Journal->pending voucher | N/A | https://prnt.sc/tHWiwznK_w2p | Accounting Journal page should be pending voucher | As Expected. | Pass
| Account | Accounting Journal | High | TC_027 | checking Long Terms loan Account Number Add Adjustment Journal Approval pending voucher | UI Testing | Account->Accounting Journal->pending voucher | N/A |  | Accounting Journal page should be pending voucher | As Expected. | Pass
| Approval | Account Approval | High | TC_028 | Long Terms loan Add Adjustment Journal Approval | Functional Testing | Account->Account Approval->Journal Approval->Long Terms Loan->Action->Approve | N/A |  | Long Terms Loan Add Adjustment Journal Approval should be approve | As Expected. | Pass
| Approval | Journal Approval | High | TC_029 | Long Terms Refund Add Adjustment Journal Approval | Functional Testing | Account->Account Approval->Journal Approval->Long Terms Refund >Action->Approve | N/A | https://prnt.sc/PUYh_iX8085f | Long Terms Refund Add Adjustment Journal Approval should be approve | As Expected. | Pass
| Account | Journal Approval | High | TC_030 | checking Account Journal Details Trans Number Long Terms Loan and Long Terms Refund | Functional Testing | Account->Accounting Journal | N/A | https://prnt.sc/LGKbgML-C8Xz | Account Journal Details Trans Number Long Terms Loan and Long Terms Refund should be showing | As Expected. | Pass
| Account | Finance and Banking | High | TC_031 | checking loan page in General Ledger Report narration showing | UI Testing | Account->Finance and Banking->Loans>GL Long Terms Loan | Account No: 100000000999 | https://prnt.sc/h2VZmJX3mKJp | General Ledger Report narration should be showing | As Expected. | Pass
| Account | Finance and Banking | High | TC_032 | Checking specific Account Loans Details in page | UI Testing | Account->Finance and Banking->Loans>Actions-View | Account No: 100000000999 | https://prnt.sc/z_VIc07uJtxI | specific Account Loans Details in page narration should be showing | As Expected. | Pass
2024-11-24 | Subcategory DDL in inventory report is empty | [10 empty] | Pass
| Inventory | Inventory Report | High | TC_033 | Try to Inventory Report Item Category type dropdown manu work or not | Functional Testing | Inventory->Inventory Report->View By->Select Item Category | View By: Inventory Report Office:All Warehouse (Location):All Item Type:ALL Item Cateory:HEALTH FOOD | https://prnt.sc/y4aMJIc9Sa2Y | Item Category type dropdown manu should be show list | As Expected. | Pass
| Inventory | Inventory Report | High | TC_034 | Try to Inventory Report Item Category filtering in Sub Category | Functional Testing | Inventory->Inventory Report->View By->Select Item Category->Sub category->Minor category->View | View By: Inventory Report Office:All Warehouse (Location):All Item Type:ALL Item Category: TestBySam Sub Category:TestBySam Minor Category: TestBySam | https://prnt.sc/GtXpcOZKISdx | Item Category after filtering should be showing in Sub Category | As Expected. | Pass
| Configuration | Item profile | High | TC_035 | Try to showing Item Category in Table View point | Functional Testing | Configuration->Item profile->Category->Table View->TBySam | Item: Category Tree View: TBySam Sub Category:TestBySam Minor Category:Testbysam | https://prnt.sc/nleeCBRgk8ee | Item Category in Table View should be showing | As Expected. | Pass
| Configuration | Item profile | High | TC_036 | Try to showing Item Category in Tree View point | Functional Testing | Configuration->Item profile->Category->Tree View->TBySam | Item: Category Tree View: TBySam Sub Category:TestBySam Minor Category:Testbysam | https://prnt.sc/gcPbzLDoHfDW | Item Category in Tree View should be showing | As Expected. | Pass
2024-12-02 | Configuration | Item profile | High | TC_037 | Try to create Serial item profile | Functional Testing | Configuration->Item profile->Add item->Serial->fillup create item->Save | Master Item code: SL 212 Master Item name: Book (SET) UOM: SET Customer:abc (01558102053) |  | IT should be seccessfully created | As Expected. | Pass
| Configuration | Item profile | High | TC_038 | check to showing item profile in serial Item Name | UI Testing | Configuration->Item profile |  | https://prnt.sc/r5Z1-AU6M7TY | IT should be showing item profile list | As Expected. | Pass
| Purchase | Purchase Receive | High | TC_039 | Try to request Purchase Receive Serial item profile | Functional Testing | Purchase->Purchase Receive->Add Direct Receive->Create Direct Receive fillup form->Save | Create Date:12/02/2024 Office:MGM Head Office Warehouse:MGM Warehouse bd Item Type:Inventory Item Select Supplier:1234 (2131211) Item: SL 212 - Book (SET) Quantity:5 Rate (WST):4 |  | It should be Purchase Receive Serial item profile created | As Expected. | Pass
| Purchase | Purchase Receive | High | TC_040 | check to showing Purchase Receive Serial item profile | UI Testing | Purchase->Purchase Receive->Receive PO->Action view |  | https://prnt.sc/5FayKvwh9ZGR | IT should be showing Purchase Receive Serial item profile list | As Expected. | Pass
| Purchase | Purchase Return | High | TC_041 | Try to Purchase partial Return Supplier serial item profile | Functional Testing | Purchase->Purchase Return-Return->partial->Return Quantity->Select Item Name->save | Return Quantity:2 Select Item Name:slb5, slb5 |  | should be Purchase partial Return successfully created | As Expected. | Pass
| Purchase | Purchase Return | High | TC_042 | Checking Purchase Return in retuen list page | UI Testing | Purchase->Purchase Return-Return list |  |  | Purchase Return should be showing in retuen list page | As Expected. | Pass
| Approval | Purchase Return Approval | High | TC_043 | Try to Purchase Return Approval | Functional Testing | Approval->Purchase Approval->Purchase Return Approval->select-Approve->yes |  |  | Purchase Return should be approve | As Expected. | Pass
| Sales | Sales Delivery | High | TC_044 | Try to Create sales Direct Delivery | Functional Testing | Sales->Sales Delivery->Create Direct Delivery fillup form->save | Create Date:12/02/2024 Office:MGM Head Office Warehouse:MGM Warehouse bd Customer:abc (01558102053) Ship To:abf edited [ mohammadpur ] Contact To:Rafsana SEcond Contact Sales Force:Etu Mahmuda Era(01928374) Item:SL 212 - Book (SET) Quantity:3 Unit Price:5 |  | Direct Delivery should be successfully Created | As Expected. | Pass
| Sales | Sales Delivery | High | TC_045 | Try to confrim in Sales Delivery list | Functional Testing | Sales->Sales Delivery->Delivery list->action --view->confrim->yes | Remark: test |  | it will should be confrim in Sales Delivery | As Expected. | Pass
| Sales | Sales Return | High | TC_046 | Try to Sales Partial Return | Functional Testing | Sales->Sales Return->Return-Partial->select iteem->save | Return Date:12/02/2024 Office:MGM Head Office Warehouse:GM Warehouse bd Return Reason:for test Return QTY:2 select serital one |  | it should be Sales Partial return | As Expected. | Pass
| Approval | Sales Return Approval | High | TC_047 | Try to Sales Return approvvel | Functional Testing | Approval->Sales Return Approval->select-Approve->yes |  |  | sales retuen should be approve | As Expected. | Pass
| Inventory | Transfer | High | TC_048 | Try to create Direct Transfer Out serial Item | Functional Testing | Inventory->Transfer->Direct Transfer fillup form->save | From Office:MGM Head Office From Warehouse:MGM Warehouse bd To Office:Rangpur Office Remarks:Test Item Name:SL 212 - Book (SET) Select item: SLB3, SLB4 |  | Direct Transfer Out serial Item should be created | As Expected. | Pass
| Approval | Transfer Return Approval | High | TC_049 | Try to Transfer Return List Approval | Functional Testing | Approval->Transfer Return List Approval->select Return->Action->select Item Name->Approvev | Return Code:ITR-M241200001 Item Code:SL 212 Item Name:Book Return Qty:2 |  | should be Transfer Return List Approve | As Expected. | Pass
| Inventory | Transfer In | High | TC_050 | Try to Transfer In serial Item | Functional Testing | Inventory>Transfer-Transfer In Transit->Action->Transfer In fillupform ->selectitem name->save | From Office:MGM Head Office From Warehouse:MGM Warehouse bd To Office:Rangpur Office To Warehouse:Rangpur Warehouse One Narration:test Receive Qty:3 Item Name:Book Select Book: SLB2,SLB3,SLB4 |  | it should be Transfer In serial Item | As Expected. | Pass
| Inventory | Dispose | High | TC_051 | Try o disposal out in serial Item | Functional Testing | Inventory->Stock Adjustment->create->Dispose fillup form ->select item name->save | Created Date:12/02/2024 Office:MGM Head Office Warehouse:MGM Warehouse bd Remarks:for test Item:SL 212 - Book (SET) Item Name Book: SLB7,SLB8 Current Stock:3 Dispose Of Qty:2 |  | it should be Dispose In serial Item | As Expected. | Pass
| Approval | stock adustment approval | High | TC_052 | Try to stock adustment approval | Functional Testing | Approval->Inventory Approval->stock adustment approval-> Action-> Approve ->yes |  |  | It should be stock adustment approve | As Expected. | Pass
| Inventory | Inventory Report | High | TC_053 | Try to serial item profile Inventory Report Item Details | Functional Testing | Inventory->Inventory Report->search->Closing Qty->Item Details | Search: SL 212 View By:Inventory Report Item:Book Closing Qty:4 | https://prnt.sc/NX9_zNSlQhY0 | Should be serial item profile Inventory Report Item Details | As Expected. | Pass
| Accounting | Accounting Journal | High | TC_054 | Checking serial item profile Account Journal Details | UI Testing | Accounting->Accounting Journal |  |  | Should be showing in account journal details | As Expected. | Pass
| Configuration | Item profile | High | TC_055 | Try to create Batch item profile | Functional Testing | Configuration->Item profile->Add item->Batch->fillup create item->Save | Master Item code:BT 212 Master Item name:bookshelf UOM: SET Customer:abc (01558102053) | https://prnt.sc/o2Cm9HgF0Pz0 | IT should be seccessfully created | As Expected. | Pass
| Configuration | Item profile | High | TC_056 | check to showing item profile in batch Item Name | UI Testing | Configuration->Item profile |  |  | IT should be showing Batch item profile list | As Expected. | Pass
| Purchase | Purchase Receive | High | TC_057 | Try to request Purchase Receive Batch item profile | Functional Testing | Purchase->Purchase Receive->Add Direct Receive->Create Direct Receive fillup form->Save | Create Date:12/02/2024 Office:MGM Head Office Warehouse:MGM Warehouse bd Item Type:Inventory Item Select Supplier:1234 (2131211) Item:BT 212 - bookshelf(SET) Quantity:15 Rate (WST):5 Name:bookshelf - SET Create Batch/Lot No: Batch bookshelf One Quantity:10 Create Batch/Lot No: Batch bookshelf Two Quantity:5 | https://prnt.sc/GtONixSIz2ly | It should be Purchase Receive Batch item profile created | As Expected. | Pass
| Purchase | Purchase Receive | High | TC_058 | check to showing Purchase Receive Batch item profile | UI Testing | Purchase->Purchase Receive->Receive PO->Action view |  | https://prnt.sc/iNerL8S602C6 | IT should be showing Purchase Receive Batch item profile list | As Expected. | Pass
| Purchase | Purchase Return | High | TC_059 | Try to Purchase partial Return Supplier batch item profile | Functional Testing | Purchase->Purchase Return-Return->partial->Return Quantity->Select Item Name->save | Batch/Lot No.: Batch bookshelf One Warehouse:MGM Warehouse bd Transaction Type:Transaction Type Quantity:2 |  | should be Purchase partial Return successfully created | As Expected. | Pass
| Purchase | Purchase Return | High | TC_060 | Checking Purchase Return in retuen list page | UI Testing | Purchase->Purchase Return-Return list |  |  | Purchase Return should be showing in retuen list page | As Expected. | Pass
| Approval | Purchase Return Approval | High | TC_061 | Try to Purchase Return Approval | Functional Testing | Approval->Purchase Approval->Purchase Return Approval->select-Approve->yesApproval->Purchase Approval->Purchase Return Approval->select-Approve->yes |  |  | Purchase Return should be approve | As Expected. | Pass
2024-12-03 | Sales | Sales Delivery | High | TC_062 | Try to Create sales Direct Delivery | Functional Testing | Sales->Sales Delivery->Create Direct Delivery fillup form->save | Create Date- 12/03/2024 Office- MGM Head Office Warehouse- MGM Warehouse bd Customer- abc (01558102053) Ship To- abf edited [ mohammadpur ] Contact To- Rafsana SEcond Contact Sales Force- Etu Mahmuda Era(01928374) Item- BT 212 - bookshelf (SET) Quantity- 1 Unit Price- 5 Serial/Batch- Batch bookshelf One Quantity- 1 |  | Direct Delivery should be successfully Created | As Expected. | Pass
2024-12-04 | Sales | Sales Delivery | High | TC_063 | Try to confrim in Sales Delivery list | Functional Testing | Sales->Sales Delivery->Delivery list->action --view->confrim->yes | Remark: test |  | it will should be confrim in Sales Delivery | As Expected. | Pass
| Sales | Sales Return | High | TC_064 | Try to Sales Partial Return | Functional Testing | Sales->Sales Return->Return-Partial->select iteem->save | Return Date:12/02/2024 Office:MGM Head Office Warehouse:GM Warehouse bd Return Reason:for test Return QTY:2 select serital one |  | it should be Sales Partial return | As Expected. | Pass
2024-12-04 | Sales | Create Sales Quotation | High | TC_065 | Try to Create Sales Quotation Sales Requisition Quotation Type with VAT | Functional Testing | Sales->Sales Quotation->Create Sales Quotation fillup form->VAT add->save | Create Date:12/04/2024 Office:MGM Head Office Customer:abc (01558102053) Quotation Type:Sales Requisition Billing Address:481/2/A , West Shewrapara , Mirpur Billing Contact Person:Rafsana Kabir Valid Till Date:2-12-2024 Item:A8 - Yale Video Door Phone (PCS) Qty:1 Unit Price:100 Value Added Tax (%):15 |  | it should be successfully Create Sales Quotation | As Expected. | Pass
| Sales | Create Sales Quotation | High | TC_066 | Try to Create Sales Quotation Sales Requisition Quotation Type without VAT | Functional Testing | Sales->Sales Quotation->Create Sales Quotation fillup form->save | Create Date:12/04/2024 Office:MGM Head Office Customer:abc (01558102053) Quotation Type:Sales Requisition Billing Address:481/2/A , West Shewrapara , Mirpur Billing Contact Person:Rafsana Kabir Valid Till Date:2-12-2024 Item:A8 - Yale Video Door Phone (PCS) Qty:1 Unit Price:100 |  | it should be not Create Sales Quotation | As Expected. | Pass
| Sales | Create Sales Quotation | High | TC_067 | Try to Sales Quotation edit item and with VAT | Functional Testing | Sales->Sales Quotation->Create Sales Quotation fillup form->save | Create Date:12/04/2024 Office:MGM Head Office Customer:abc (01558102053) Quotation Type:Sales Requisition Billing Address:481/2/A , West Shewrapara , Mirpur Billing Contact Person:Rafsana Kabir Valid Till Date:2-12-2024 Item:A8 - Yale Video Door Phone (PCS) Qty:1 Unit Price:100 Value Added Tax (%):10 |  | it should be edited successfully Sales Quotation | As Expected. | Pass
2024-12-04 | Configuration | Item profile | High | TC_068 | Checking Item Type drop down option showing same Item Type list in item profile page | Functional Testing | Configuration->Item profile->Item Type->view | Item Type:Raw Material |  | Should be Item Type drop down option showing same Item Type list in item profile page | As Expected. | Pass
| Configuration | Item profile | High | TC_069 | Checking SL No Filter in Item profile when switching page | Functional Testing | Configuration->Item profile->Item Type->view->Filter button | Item Type:Raw Material Range:100 Filter: 101-200 |  | Should be SL No showing Filter in Item profile when switching page | As Expected. | Pass
2024-12-08 | MGM-7443 Configuration | Item profile | High | TC_070 | Verify the functionality to create a new item wth weght. | Functional Testing | Configuration->Item->Add Item->fillup the form->Save | Master Item Code: C121 Master Item Name: Coffee Printed Item Name: Coffee Item Type: Finished/Trading Goods UOM: PCS Net Weight UOM: PCS Net Weight Unit: 1000 |  | The new item is visible in the item listing page with all fields displayed correctly. | As Expected. | Pass
2024-12-09 | MGM-7443 Purchase Order | Item profile | High | TC_071 | Verify new item visibility on Item Profile page | UI Testing | Configuration->Item Profile |  |  | The new item is displayed in the item list on the Item Profile page. | As Expected. | Pass
| MGM-7443 Purchase Order | foreign Purchase | High | TC_072 | Verify Creation of Item Profile Within a Foreign Purchase Order | Functional Testing | Purchase-> Purchase Order->foreign PO->Create foreign Purchase->fillup form->save | Create Date: 12/09/2024 Office: Select MGM Head Office Inventory Type: Inventory Item Supplier: PRT-M0054 - A rat (78899985) Urgency: Medium Expected Receive Date: 12/09/2024 Item: t 342 - cap(PCS) Quantity: 7.000000 Rate (BDT): 10 |  | The Purchase Order is successfully created and saved in the system. | As Expected. | Pass
| MGM-7443 Purchase Order | foreign Purchase | High | TC_073 | Verify New Foreign Purchase Order (PO) Appears in Purchase Order Page | UI Testing | Purchase-> Purchase Order->foreign PO |  |  | The newly created foreign Purchase Order appears in the Purchase Order list. | As Expected. | Pass
| MGM-7443 Approval | Purchase Approval | High | TC_074 | Verify the approval process for a foreign Purchase Order. | Functional Testing | Approval->Purchase Order Approval->foreign PO Approval->select->Approve |  |  | The approved PO appears in the Purchase Order list under the "Approved" status. | As Expected. | Pass
| MGM-7443 Purchase Order | foreign PO | High | TC_075 | Verify the creation of shipment for a foreign Purchase Order. | Functional Testing |  |  |  | The shipment status is updated to Created or equivalent. | As Expected. | Pass
| MGM-7443 Approval | Shipment Approval | High | TC_076 | Verify the approval process for a shipment in a foreign Purchase Order. | Functional Testing | Approval->Purchase Order Approval->Shipment Approval ->select->Approve |  |  | The Purchase Order status is updated to reflect the shipment approval | As Expected. | Pass
| MGM-7443 Purchase | Purchase Receive | High | TC_077 | Verify the Purchase Receive process for a foreign Purchase Order. | Functional Testing | Purchase-Purchase Receive-Actions-fillup form-Receive | Rcv. QTY: 2 |  | he system updates the Purchase Order status to Received. | As Expected. | Pass
| MGM-7443 Purchase Report | Foreign Purchase | High | TC_078 | Verify the Checkbox Field for Net Weight in the Foreign Purchase Details Report | Functional Testing | Purchase-Purchase Report-foreign Purchase-Net Weight-view |  | https://prnt.sc/M9NpFi1jpd9q | The system should display any relevant Net Weight data for products, such as weights in kilograms or pounds, for the appropriate Foreign Purchase Orders. | As Expected. | Pass
| MGM-7443 Purchase Report | Foreign Purchase | High | TC_079 | Verify Removal of Net Weight Column When Checkbox is Unchecked in Foreign Purchase Details Report | Functional Testing | Purchase-Purchase Report-foreign Purchase-view |  | https://prnt.sc/rdquIeklg4xI | The report should be generated without any errors or performance issues when the checkbox is unchecked | As Expected. | Pass
2024-12-10 | MGM-7523 Purchase | Create Purchase Requisition | High | TC_080 | Try to Create Purchase Requisition for an Inventory Service Item | Functional Testing | Purchase -Purchase Requisition- Create Purchase Requisition-fillup the form-save | Employee Tonmoy Datta (01716948) Office MGM Head Office Warehouse MGM Warehouse bd Inventory Type Service Item Expected Date 12/10/2024 Item 55 - LP Gas (PCS) Current Stock 8 Request Quantity 1 Rate 10 | https://prnt.sc/GTnus9jRUAAV | The Purchase Requisition should be successfully created . | As Expected. | Pass
| MGM-7523 Purchase | Purchase Requisition | High | TC_081 | Verify Visibility of New Purchase Requisition in the Requisition List | UI Testing | Purchase -Purchase Requisition |  | https://prnt.sc/hJ_nNWSJZu69 | The requisition list page displays the newly created purchase requisition. | As Expected. | Pass
| MGM-7523 Approval | Purchase Requisition Approval | High | TC_082 | Verify Purchase Requisition Approval Process Using PR Code | Functional Testing | Approval-Purchase Approval-Purchase Requisition Approval-select-Approve-yes |  |  | It should be successfully Approve Purchase Requisition | As Expected. | Pass
| MGM-7523 Purchase Order | Create Purchase Order | High | TC_083 | Try to Create Purchase Order with Purchase Requisition. | Functional Testing | Purchase -Purchase Order- Local PO-Create Purchase Order-select Create From Requisition -select Purchase Requisition-fillup the form-save | select Create From Requisition Create Date 12/10/2024 Office MGM Head Office Purchase Requisition PR-M241200032 Inventory Type Service Item Supplier PRT-M0082 - ACI (456) Urgency Medium Expected Receive Date 12/10/2024 | https://prnt.sc/g6F0x3esAduf | The Purchase Order should be successfully created . | As Expected. | Pass
| MGM-7523 Approval | Purchase Order Approval | High | TC_084 | Verify Purchase Order Approval Process Using PO Code | Functional Testing | Approval-Purchase Approval-Purchase Order Approval-select-Approve-yes |  | https://prnt.sc/EB429KSf_sPk | It should be successfully Approve Purchase Order | As Expected. | Pass
| MGM-7523 Purchase Receive | Approve PO | High | TC_085 | Verify Mandatory Expense Selection with PO Number in Receive Order Process | Functional Testing | Purchase -Purchase Receive- Approve PO-select PO Number Actions-Expense field-save | Expense Expense of Card Rcv. QTY 1 | https://prnt.sc/woR3Svrxuf-u | It should be Receive Expense Selection Mandatory with PO Number. | As Expected. | Pass
| MGM-7523 Purchase Receive | Receive PO | High | TC_086 | Verify Purchase Received Details showing with PO Number. | Functional Testing | Purchase -Purchase Receive- Receive PO-select PO Number Actions-Purchase Received Details |  | https://prnt.sc/SXWRGWuad_U2 | It should be successfully displays purchase received details when searched using a valid PO number. | As Expected. | Pass
2024-12-11 | MGM-7563 Sales Order | Create Sales Order | High | TC_087 | Try to Create Sales Order | Functional Testing | Sale-Sales Order-Create Sales Order-fillup form-save | Create Date: Enter 12/11/2024. Office: MGM Head Office. Customer: ABDUL MONEM LIMITED (32 125761939) from the dropdown. Ship To: the address Monem Business District 111, Bir Uttam C.R. Dutta Road, Level – 13. Contact To: Enter Akbar 63. Sales Force: Asaduzzaman. Type: Sales. Exp. Delivery Date: Enter 12/11/2024 Item- Customer rwetrytytyrtwre - xiamio --0071324456 (PCS) Quantity (PCS) - 3 Rate- 8 |  | MGM-7563 Approval | As Expected. | Pass
| MGM-7563 Approval | Sales Approval | High | TC_088 | Verify Sales Order Approval Process | Functional Testing | Approval-Sales Approval-Sales Order Approval-select-Approve-yes |  |  | It should be successfully Approve Sales Order | As Expected. | Pass
| MGM-7563 Purchase Receive | Direct Receive / Direct Purchase | High | TC_089 | Try to Direct Receive / Direct Purchase tagging with SO | Functional Testing | Purchase -Purchase Receive-Direct Receive / Direct Purchase -select Create From Sales Order-fillup form-save | Select Create From Sales Order Sales Order- SO-M241200174 Customer-ABDUL MONEM LIMITED Office- MGM Head Office Warehouse-MGM Warehouse bd Item Type- Inventory Item Select Supplier - 1234 (2131211) Receive Qty- 8 Rate (WST)- 9 |  | It should be successfully Direct Receive / Direct Purchase | As Expected. | Pass
| MGM-7563 Purchase Receive | Receive PO | High | TC_090 | Verify Purchase Received Details showing with PO Number/GRN | Functional Testing | Purchase -Purchase Receive- Receive PO-select PO Number Actions-Purchase Received Details |  |  | It should be successfully displays purchase received details when searched using a valid PO number./ GRN | As Expected. | Pass
| MGM-7563 Sales | Sales Report | High | TC_091 | Verify Sales Report Details like:(Sales Qty,Sales Order Amount,Purchase Qty,COGS/Purchase Amount) showing with SO. | Functional Testing | Sale-Sales Report-View By View By Order Wise Profit/Margin-fillup form-view |  |  | It should be showing Sales Report Details like:(Sales Qty,Sales Order Amount,Purchase Qty,COGS/Purchase Amount) | As Expected. | Pass
2024-12-11 | MGM-7527 Purchase Order | Create Purchase Order | High | TC_092 | Try to Create Purchase Order | Functional Testing | Purchase -Purchase Order- Local PO-Create Purchase -fillup the form-save | Create Date 12/10/2024 Office MGM Head Office Inventory Type Service Item Supplier PRT-M0082 - ACI (456) Urgency Medium Expected Receive Date 12/10/2024 |  | The Purchase Order should be successfully created . | As Expected. | Pass
| MGM-7527 Approval | Purchase Order Approval | High | TC_093 | Try to Purchase Order Approval | Functional Testing | Approval-Purchase Approval-Purchase Order Approval-select-Approve-yes |  |  | It should be successfully Approve Purchase Order | As Expected. | Pass
| MGM-7527 Purchase Receive | Approve PO | High | TC_094 | Verify Mandatory Expense Selection with PO Number in Receive Order Process | Functional Testing | Purchase -Purchase Receive- Approve PO-select PO Number Actions-Expense field-save |  |  | It should be Receive Expense Selection Mandatory with PO Number. | As Expected. | Pass
| MGM-7527 Purchase Receive | Receive PO | High | TC_095 | Verify Purchase Received Details showing with PO Number. | Functional Testing | Purchase -Purchase Receive- Receive PO-select PO Number Actions-Purchase Received Details |  |  | It should be successfully displays purchase received details when searched using a valid PO number. | As Expected. | Pass
| MGM-7527 Approval | Purchase Bill Approval | High | TC_096 | Try to pending bill Approval with PO | Functional Testing | Approval-Purchase Approval-Purchase Bill Approval-select-Approve-yes |  |  | It should be successfully Approval with PO | As Expected. | Pass
| MGM-7527 Purchase Payment | Due list | High | TC_097 | Try to Bill Payment customer wise include attachtment file | Functional Testing | Purchase Payment-Due List-action-Bill Payment-include attachtment-fillup form-save |  | Office--MGM Head Office Select -Cash attachtment file: pic.jpg | It should be successfully include attachtment file in customer wise | As Expected. | Pass
| MGM-7527 Purchase Payment | Pending Bill | High | TC_098 | Try to Pending Supplier Bill details wise include attachtment file | Functional Testing | Purchase Payment-Pending Bill--action--include attachtment-fillup form-save |  | Office--MGM Head Office Select -Cash attachtment file: pic1.jpg | It should be successfully include attachtment file in Supplier wise | As Expected. | Pass
| MGM-7527 Purchase Payment | Paid GRN/Bill | High | TC_099 | Verify include attachtment file view in paid GRN / bill | Functional Testing | Purchase Payment-Paid GRN/ Bill-action-view-save |  |  | It should be successfully showing include attachtment file. | As Expected. | Pass
2024-12-12 | MGM-7609 | Production Details Report | High | TC_100 |  | Functional Testing |  |  |  |  | As Expected. | Pass
| MGM-7609 Production | Create BOM | High | TC_101 | Try to create multiple Bom & single Bom | Functional Testing | production-Bill Of Material-Create Bill Of Material-fillup the form-save |  |  | It should be created successfully multiple Bom & single Bom | As Expected. | Pass
| MGM-7609 Production | Production Order | High | TC_102 | Try to create Production Order | Functional Testing | production-Production Order-Create Production Order-fillup the form-save |  |  | It should be created successfully Production Order |  | Pass
| MGM-7609 Approval | Approval Production Order | High | TC_103 | Try to Approval Production Order | Functional Testing | Approval-Production Order Approval-Order Approval-select-Approve-yes |  |  | It should be successfully Approve Production Order | As Expected. | Pass
| MGM-7609 Approval | Approval Item Requisition | High | TC_104 | Try to Item Requisition Approval with Production Order | Functional Testing |  |  |  |  | As Expected. | Pass
2024-12-17 | MGM-7651 configuration | Item create | High | TC_105 | Try to Create Item profile with Plastics Division | Functional Testing | configuration-add Item-AutoBarCode-select Division-select Category-fillup form-save |  | Master Item name-mouse onee Department - Plastics Category- test one Sub Category-test two Minor Category-test three Tag Customer-PRT-M0211 - akasaash (0179453555) | It should be successfully Create Item profile with Division | As Expected. | Pass
| MGM-7651 configuration | Item create | High | TC_106 | Try to Create Item profile with metral Division | Functional Testing | configuration-add Item-AutoBarCode-select Division-select Category-fillup form-save |  | Master Item name-cablee Department - metral Category-metral one Sub Category-metral two Minor Category-metral three Tag Customer-PRT-M0211 - akasaash (0179453555) | It should be successfully Create Item profile with Division | As Expected. | Pass
| MGM-7651 Sales Delivery | Create Direct Delivery | High | TC_107 | Try to Create Direct Delivery with Plastics Division Item | Functional Testing | Sales -Sales Delivery-Create Direct Delivery-select depetment Item- fillup form-save |  | Office-MGM Head Office Warehouse-MGM Warehouse bd Customer -555555 - Akash Dhaka (01705280423) Item -mouse onee Quantity -4 Unit Price-10 | It should be successfully Create Direct Delivery | As Expected. | Pass
| MGM-7651 Sales Delivery | Direct Delivery | High | TC_108 | Try to Direct Delivery confirm | Functional Testing | Sales -Sales Delivery-Delivery list-action -confirm |  | Sales -Sales Collection -due list-view-Actions-Cash Type-select Invoice-Collection amount-save | It should be successfully Direct Delivery confirm | As Expected. | Pass
| MGM-7651 Sales Collection | Due list | High | TC_109 | Try to Sales Collection in due list | Functional Testing | Sales -Sales Collection -due list-view-Actions-Cash Type-select Invoice-Collection amount-save |  | Office-MGM Head Office Cash Type -Cash in hand Invoice-SD-M241200140 Collection-50 | It should be successfully due list in Sales Collection | As Expected. | Pass
| MGM-7651 Sales Collection | Bill Create | High | TC_110 | Try to Sales Collection in Bill Create | Functional Testing | Sales -Sales Collection -Bill Create-fillup form-select Invoice -Create Bill |  | Office -MGM Head Office Customer -AAA (32556789899) Invoice No- SD-M241200022 |  |  | Pass
| MGM-7651 Sales Collection | Collection by Invoice | High | TC_111 | Try to Sales Collection in Collection by Invoice | Functional Testing | Sales -Sales Collection -Collection by Invoice-fillup form-select Customer/Invoice -save |  | Office-MGM Head Office Cash Type-Cash in hand Customer-Akashh Invoice -SD-M240200037 Collection Amount- 22 |  | As Expected. | Pass
| MGM-7651 Sales Collection | Collected Invoice | High | TC_112 | Try to Sales Collection in Collected Invoice | Functional Testing | Sales -Sales Collection -Collected Invoice -Collection Amount |  |  |  | As Expected. | Pass
| MGM-7651 Sales Collection | Due Invoice | High | TC_113 | Try to Sales Collection in Due Amount with Invoice No | Functional Testing | Sales -Sales Collection -Due Invoice-select Invoice -Due Amount |  |  |  | As Expected. | Pass
| MGM-7651 Sales Report | Sales Report | High | TC_114 | Try to showing Month Wise Sales vs Collection Report in Sales Report summary and check box Sales Report details | Functional Testing | Sales -Sales Report -select View By-View |  | View By-Month Wise Sales VS Collection Year-2024 From Month-December To Month-December Item Category-test one Customer Group-All Customer-Akash |  | As Expected. | Pass
| MGM-7651 Sales Report | Sales Report | High | TC_115 | Try to Month Wise Sales vs Collection Report in Sales Report summary without (Item Category, Customer Group Customer)Sales Report details | Functional Testing | Sales -Sales Report -select View By- without check box-View |  | View By-Month Wise Sales VS Collection Year-2024 From Month-December To Month-December Item Category- Customer Group- Customer- | it should showing with Unassigned issue and division together month wise sales report | As Expected. | Pass
| MGM-7651 Sales Report | Sales Report | High | TC_116 | Try to Month Wise Sales vs Collection Report in summary Unassigned issue showing non-division item | Functional Testing | Sales -Sales Report -select View By- without check box-View |  | View By-Month Wise Sales VS Collection Year-2024 From Month-December To Month-December Item Category- Customer Group- Customer- | it should be showing non-division item Unassigned issue with month wise sales report | As Expected. | Pass

## Bug Report
SL | 2 | Task No | Client Name | Issue/bug Details | Status | Type | Tester name | Product Name | Developer name | Remarks
bug_01 | 2024-04-29 | MGM-4192 |  | fund transfer office filter if change pagination then need to do filter again | [5 empty] | MGM BUG Reprot Summary from | 2024-04-30
[10 empty] | Toal issue found | 1
bug_01 | 2024-11-26 |  | Apon |  | Pending | Issue | Tanmoy | Managerium | Akash | Toal bug found | 0
Issue/Bug breakdown
[10 empty] | Solved | 0
[10 empty] | Pending | 1
[10 empty] | In Progress | 0
[10 empty] | Reject | 0
Managerium
Managerium